## Sheet1
ID | Phase/Milestone | Task Description | Collaborator | Status
P1 | Phase 1: Data Acquisition & Setup | Milestone 1: DB Schema Finalized & Sources Confirmed | Collaborative | Completed
P1.1 | Environment Setup | Finalize PostgreSQL instance setup (Local/Cloud) and PostGIS extension installation. | Jainil | Not started
P1.2 | Data Storage | Design and create the complete SQL database schema (tables for location, traffic, weather). | Kalpan | Not started
P1.3 | Data Acquisition | Develop Python scripts for fetching/parsing Google Traffic API data (time-series). | Adit | Not started
P1.4 | Data Acquisition | Download/Process Kaggle, Boston Open Data, MassDOT static datasets. | Kalpan | Not started
P2 | Phase 2: Data Cleaning & Preprocessing | Milestone 2: Data Acquisition & DB Population Complete | Collaborative | Not started
P2.1 | Data Merging | Write Python pipeline to merge all four data sources based on location and timestamp. | Jainil | Not started
P2.2 | Data Cleaning | Implement Python script for missing value handling and categorical encoding (e.g., weather types). | Adit | Not started
P2.3 | DB Population | Execute cleaning pipeline and populate "Cleaned" tables in PostgreSQL. | Kalpan | Not started
P3 | Phase 3: Analysis & Reporting | Milestone 3: Data Cleaning Pipeline Executed | Collaborative | Not started
P3.1 | Analytical Report | Write & Test SQL Query: Identifying peak congestion times and locations. | Kalpan | Not started
P3.2 | Analytical Report | Write & Test SQL Query: Quantifying correlation between weather and slowdowns. | Adit | Not started
P3.3 | Analytical Report | Write & Test remaining 6 Analytical SQL Reports (e.g., historical trends, comparison to global benchmarks). | Jainil | Not started
P4 | Phase 4: Predictive Modeling (Initial) | Milestone 4: Advanced SQL Reports Completed | Collaborative | Not started
P4.1 | Model Development | Develop baseline predictive model (scikit-learn) for travel time (A to B) using clean data. | Adit | Not started
P4.2 | Model Evaluation | Generate report on model performance: predicted vs. actual output and error metrics. | Jainil | Not started
P5 | Phase 5: Finalization | Milestone 5: Final Report & Presentation | Collaborative | Not started
P5.1 | Final Report | Draft and finalize the comprehensive report, integrating all findings and model results. | Kalpan | Not started
P5.2 | Presentation | Prepare and rehearse the final project presentation. | Collaborative | Not started